## Sheet1
WPs | DELIVERABLES | ACTIVITIES | Weeks | М1 | М2 | М3 | М4 | М5 | М6 | М7 | М8 | М9 | М10 | М11 | М12 | М1 | М2 | М3 | М4 | М5 | М6 | М7 | М8 | М9 | М10 | М11 | М12 | М1 | М2 | М3 | М4 | М5 | М6 | М7 | М8 | М9 | М10 | М11 | М12
WP1 | D1.1. Business community needs, and expectations analyzed. | A1.1.1. Business community focus-groups | 6 |  | 2x | 2x | 2x
|  | A1.1.2. Business community semi-structured interviews | 6 |  | 2x | 2x | 2x
| D1.2. Current situation at RU and IN universities concerning engineering and science curricula analyzed. | A1.2.1. Survey of RU and IN universities | 8 |  | 4x | 4x
|  | A1.2.2. Evaluation visits | 1 |  |  |  | 0.5x | 0.5x
|  | A1.2.3. Assessment report on current situation at RU and IN universities | 3 |  |  |  |  | 3=
| D1.3. The list of selected and assigned engineering and science curricula to modernize. | A1.3.1. Selection and assignment of curricula | 1 | [5 empty] | 1x
WP2 | D2.1. Modernized curricula (IPS educational trajectory (idea–project–start-up) developed). | A2.1.1. Development of IPS educational trajectory (idea–project–start-up) | 8 | [6 empty] | 1=3x | 4x
|  | A2.1.2. Modernization of master’s research activity | 4 | [7 empty] | 4x
| D2.2. Modernized syllabi of IPS educational trajectory. | A2.2.1. Development of “Introduction to entrepreneurship” course syllabus | 2 | [8 empty] | 2x
|  | A2.2.2. Development of “Idea” module syllabus | 4 | [8 empty] | 4x
|  | A2.2.3. Development of “Project” module syllabus | 4 | [9 empty] | 4x
|  | A2.2.4. Development of “Start-up” module syllabus | 4 | [9 empty] | 4x
| D2.3. Teaching materials list. | A2.3.1. Development of teaching materials | 36 | [10 empty] | 4x | 4x | 4x | 4x | 4x | 4x | 4x | 4x | 4x
WP3 | D3.1. Networking competences university partners teachers. | A3.1.1. Training in networking competences | 4 |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x
|  | A3.1.2. Series of webinars on networking competences | 4 |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
| D3.2. Instructional design and gamification implementation competencies. | A3.2.1. Series of training on instructional design and gamification | 4 |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x |  |  |  | x
WP4 | D4.1. Curriculum modernization implementation approved at each RU and IN university. | A4.1.1. Administrative procedures enabling pilot implementation | 3 | [15 empty] | x | x | x | x | x | x | x
| D4.2. Curriculum implemented. | A4.2.1. Pilot implementation of curricula | 20 | [22 empty] | 2x | 2x | 2x | 2x | 2x | 2x | 2x | 2x | 2x | 2x
WP5 | D5.1. Quality of curriculum implementation assured. | A5.1.1. Peer-review of modernized curriculum | 2 | [8 empty] | 2x
|  | A5.1.2. Peer-review of course “Introduction to entrepreneurship” syllabi | 1 | [9 empty] | 1x
|  | A5.1.3. Peer-review of module “Idea” syllabi | 1 | [9 empty] | 1x
|  | A5.1.4. Peer-review of module “Project” syllabi | 1 | [10 empty] | 1x
|  | A5.1.5. Peer-review of module “Start-up” syllabi | 1 | [10 empty] | 1x
|  | A5.1.6. Survey of master’s students | 2 | [22 empty] | 1x | [8 empty] | 1x
|  | A5.1.7. Survey of business community representatives | 2 | [8 empty] | x | x | x
|  | A5.1.8. Analysis of surveys | 2 | [11 empty] | 1x | [20 empty] | 1x
|  | A5.1.9. Corrections | 3 | [12 empty] | 1x | [10 empty] | 1x | [9 empty] | 1x
| D5.2. Quality assurance visits. | A5.2.1. Quality assurance visits | 1 | [34 empty] | 1x
| D5.3. Quality control activities for the future defined. | A5.3.1. Quality control activities for the future | 1 | [34 empty] | 1x
| D5.4. External audit completed | A5.4.1. External audit | 2 | [32 empty] | 2x
WP6 | D6.1. Awareness of the project raised, project results disseminated | A6.1.1. Information sessions | 6 |  | 1x | [9 empty] | 1x |  |  |  | 1x | [7 empty] | 1x |  |  |  | 1x | [7 empty] | 1x
|  | A6.1.2. Dissemination conference | 1 | [34 empty] | 1x
| D6.2. Project web-site. | A6.2.1. Project web-site updates and maintenance | 4 |  | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x
WP7 | D7.1. Administrative guidelines for project management. | A7.1.1. Elaboration of the administrative guidelines | 2 | [18 empty] | 0.5x | 0.5x | 0.5x | 0.5x
| D7.2. Internal project guideline | A7.2.1. Development of internal project guideline | 2 | [10 empty] | 2x
| D7.3. Strategic management of the project. | A7.3.1. Annual F2F strategic meetings | 3 |  |  |  |  | 1x | [16 empty] | 1x | [12 empty] | 1x
|  | A7.3.2. Strategic planning and reporting | 3 |  |  |  | x | x | [5 empty] | x | x | [8 empty] | x | x | [11 empty] | x | x
|  | A7.3.3. Strategic meeting in Brussel | 1 |  |  |  |  | 1=
| D7.4. Every-day management of the project. | A7.4.1. Coordination online meetings | 3 | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x | =x
|  |  |  | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT
|  |  |  | 2018 |  | 2019 | [11 empty] | 2020 | [11 empty] | 2021

## Лист1
1 | 1.1 | 1.1.1
2 | 1.2
3 | 1.3
4 | 1.4
5 | 1.5
6 | 1.6
7 | 1.7